## Sheet1
| Risk Description | Pre Mitigation |  |  |  | Mitigation | Post Mitigation |  |  |  | % Reduce
# |  | P | T | Q | I |  | P | T | Q | I
1 | Lack of detailed information on current peak shavings technologies to be able to understand and model suitable system architectures. This could impact the quality of the modelling . | 2 | 1 | 2 | 6 | Reduce scope of model, basing model more closely on previous research and case studies. Look for alternate methods from further reading, that could solve the problem | 1 | 2 | 1 | 3 | 50%
2 | Delay's in obtaining University energy usage and cost data, from the Estates departement. This will effect the time to begin building the simulation | 1 | 2 | 1 | 3 | Request energy data from John Brenton and Chris Jones before Christmas break. Then continue to chase data, well before the scheduled time. Use general data as a placeholder for WP4.1 and continue WP4.2, 4.3, 4.4 | 1 | 1 | 1 | 2 | 33.33%
3 | Unable to obtain enough details from the University's energy data to model decentralised peak shaving system | 2 | 2 | 2 | 8 | Generate a representative model based on general industrial data and intuition from discussions with John Brenton and Chris Jones. Booking further meetings will reveal their insight into the University's energy usage data reducing assumptions and improving quality. | 1 | 2 | 2 | 4 | 50%
4 | Challenges associated in creating representative model of system, due to too much complexity in creating a detailed enough model | 3 | 2 | 1 | 9 | Seek expert advise from Mike McCann on modelling, taking additional lessons to improve Matlab skills. Find relevant people with expertise in the University and withing Arup to assist with the complexity. | 2 | 1 | 1 | 4 | 55.56%
5 | Overall delay in project timescales. This could result in WP's not being completed fully, hindering the quality of outputs in WP6 | 2 | 2 | 3 | 10 | In the case of delays, modelling work will be reduced, reducing work in WP4.3 and 4.4. The key findings from each WP will be documented thoroughly, allowing these finding conveyed for the poster presentation. | 1 | 2 | 2 | 4 | 60%